## Master_Overview
AI VOICE INTERVIEW PLATFORM - 5-MEMBER MASTER SPRINT TRACKING
Unified Deliverables Tracking across Interview Agent, Database, Evaluation, Voice, and Frontend
Task ID | Member | Module / Feature | Task Description & Deliverables | Files / Deliverables Owned | Dependencies | Est. Days | Status
M1-01 | Member 1 (Lead/You) | Interview Agent | Build zero-LLM InterviewerAgent state controller, phase management (Intro -> Tech -> Behavioral -> Wrapup), topic coverage tracking | backend/agents/interviewer.py, interview_state.py, constants.py |  | 3 | In Progress
M1-02 | Member 1 (Lead/You) | Context Injection | Implement dynamic system prompt assembly injecting Job Role, JD, Resume content, Style, and Difficulty | backend/agents/templates/interviewer_templates.py, config_models.py |  | 2 | In Progress
M1-03 | Member 1 (Lead/You) | Session Orchestrator | Build AgentSessionManager to coordinate voice turns, conversation history logging, and timer limits | backend/agents/orchestrator.py, utils/time_manager.py |  | 3 | In Progress
M1-04 | Member 1 (Lead/You) | Interview Session API | Implement REST API endpoints for session initialization, turn recording, config updates, and status checks | backend/api/agent_api.py, middleware/session_middleware.py | M2-03 | 2 | Pending
M1-05 | Member 1 (Lead/You) | Agent Integration | Wire Interviewer lifecycle with Voice Gateway & Coach triggers upon turn finalization | backend/services/session_manager.py, utils/event_bus.py | M3-02, M4-03 | 3 | Pending
M2-01 | Member 2 | Database Core Schema | Design and implement PostgreSQL schema for core session and candidate tables (users, interview_blueprints, interview_sessions, interview_questions, candidate_answers) | backend/database/schema.sql, migrations/001_core.sql |  | 3 | In Progress
M2-02 | Member 2 | Evaluation & Analytics Schema | Design and implement tables for scoring, feedback, and speech tasks (score_dimensions, scores, turn_feedback, interview_reports, recommended_resources, speech_tasks) | backend/database/schema.sql, migrations/002_analytics.sql | M2-01 | 2 | In Progress
M2-03 | Member 2 | Supabase Client & CRUD | Build DatabaseManager and MockDatabaseManager for CRUD operations across all 11 tables | backend/database/db_manager.py, mock_db_manager.py | M2-01, M2-02 | 3 | In Progress
M2-04 | Member 2 | Security & Isolation | Implement Row-Level Security (RLS) policies, UUID generation, index optimization, and updated_at triggers | backend/database/schema.sql | M2-02 | 2 | Pending
M2-05 | Member 2 | Auth & User Endpoints | Build user authentication endpoints and JWT verification middleware | backend/api/auth_api.py, backend/database/auth_helpers.py | M2-03 | 2 | Pending
M3-01 | Member 3 | Evaluation LLM Service | Configure LLM integration layer for Gemini (ChatGoogleGenerativeAI) & Groq fallback | backend/services/llm_service.py, utils/llm_utils.py |  | 2 | Pending
M3-02 | Member 3 | Per-Turn Coaching Agent | Build AgenticCoachAgent.evaluate_answer() for real-time turn feedback and STAR methodology critique | backend/agents/agentic_coach.py, templates/coach_templates.py | M3-01 | 3 | Pending
M3-03 | Member 3 | Comprehensive Scoring Engine | Implement multi-dimensional evaluation rubric (Technical, Communication, Problem Solving, Leadership) | backend/agents/evaluation_rubrics.py, score_dimensions logic | M3-02, M2-02 | 3 | Pending
M3-04 | Member 3 | Final Report Synthesis | Build end-of-interview report generator compiling scorecard, summary, strengths, and areas of improvement | backend/agents/report_generator.py, api/agent_api.py | M3-03 | 2 | Pending
M3-05 | Member 3 | Learning Resource Discovery | Integrate Serper.dev API & build LearningResourceSearchTool to find targeted tutorials based on candidate weaknesses | backend/services/search_service.py, search_helpers.py, tools/search_tool.py | M3-04 | 2 | Pending
M4-01 | Member 4 | Nova Bedrock Worker | Build Amazon Nova 2 Sonic Bedrock HTTP/2 bidirectional streaming worker process (py -3.13) | backend/services/nova_sonic_worker.py, config/__init__.py |  | 4 | In Progress
M4-02 | Member 4 | Voice Engine Orchestration | Implement NovaSonicVoiceEngine & NovaSonicSession process supervisor with 7.5m stream auto-renewal | backend/services/nova_sonic_engine.py | M4-01 | 3 | In Progress
M4-03 | Member 4 | WebSocket Voice Gateway | Build real-time WebSocket endpoint /api/speech-to-text/stream with connection tracking and audio streaming | backend/api/speech_api.py, speech/websocket_processor.py, connection_manager.py | M4-02 | 3 | In Progress
M4-04 | Member 4 | Gemini Live Voice Fallback | Implement fallback real-time voice engine using Gemini 3.8 Live API (gemini_voice_engine.py) | backend/services/gemini_voice_engine.py | M4-03 | 2 | Pending
M4-05 | Member 4 | Audio Optimization & Barge-in | Implement audio chunking (16kHz PCM in / 24kHz PCM out), barge-in handling, and echo cancellation coordination | backend/api/speech/audio_utils.py, tts_service.py | M4-03 | 2 | Pending
M5-01 | Member 5 | Interview Cockpit UI | Build active interview cockpit screen (InterviewSession.tsx, CockpitChatStream.tsx) with Theme 03 Red & Gold design | frontend/src/components/InterviewSession.tsx, CockpitChatStream.tsx |  | 3 | In Progress
M5-02 | Member 5 | WebGL Audio Visualizer | Implement WebGL GLSL real-time oscilloscope wave rendering mic audio and AI speech waves | frontend/src/components/CockpitAudioWave.tsx | M5-01 | 2 | In Progress
M5-03 | Member 5 | Web Audio Streaming Player | Build gapless PCM audio player with AudioContext and mic transmission gating to avoid echo loops | frontend/src/utils/streamingAudioPlayer.ts, hooks/useVoiceFirstInterview.ts | M5-02, M4-03 | 3 | In Progress
M5-04 | Member 5 | Post-Interview Scorecard UI | Build rich post-interview analysis dashboard with radar charts, feedback breakdown, and resource links | frontend/src/components/PostInterviewReport.tsx, TranscriptDrawer.tsx | M3-04, M5-01 | 3 | Pending
M5-05 | Member 5 | Config & Resume Upload Portal | Build candidate setup onboarding form, PDF/DOCX resume file upload, and auth modal dialogs | frontend/src/pages/Index.tsx, components/AuthModal.tsx, services/api.ts | M1-04, M2-05 | 2 | Pending

## Member_1_Interviewer
MEMBER 1: INTERVIEW AGENT & SESSION ORCHESTRATION LEAD
Scope: Zero-LLM InterviewerAgent, Context Prompt Engine, AgentSessionManager, Lifecycle APIs
Task ID | Module / Subsystem | Detailed Task Description & Deliverables | Files / Symbols Owned | Dependencies | Est. Days | Status | Sprint
M1-01 | Zero-LLM Interview Controller | Build InterviewerAgent controller with phase transitions (Introduction -> Technical -> Behavioral -> Wrapup), question counters, and topic coverage tracker | backend/agents/interviewer.py, backend/agents/interview_state.py, backend/agents/constants.py |  | 3 | In Progress | Sprint 1
M1-02 | Dynamic Prompt & Context Assembly | Implement dynamic context injection template incorporating Candidate Resume text, Job Description (JD), target role, interview style, and difficulty | backend/agents/templates/interviewer_templates.py, backend/agents/config_models.py |  | 2 | In Progress | Sprint 1
M1-03 | Agent Session Manager | Build AgentSessionManager to coordinate voice turns, update interview phases, handle idle timers, and maintain in-memory conversation history | backend/agents/orchestrator.py, backend/utils/time_manager.py |  | 3 | In Progress | Sprint 2
M1-04 | Session REST Endpoints | Implement /interview/session (creation), /interview/start (intro greeting), /interview/message (REST fallback), and /interview/status | backend/api/agent_api.py, backend/middleware/session_middleware.py | M2-03 | 2 | Pending | Sprint 2
M1-05 | Interview Termination & Timer Logic | Implement early termination conditions, 00:00 timer expiration trigger, and interview_ending event propagation to frontend | backend/agents/interviewer.py, backend/services/session_manager.py | M4-03 | 2 | Pending | Sprint 3
M1-06 | Agent Integration & Event Bus | Wire InterviewerAgent turn finalization with Voice Gateway and trigger background CoachAgent.evaluate_answer() | backend/services/session_manager.py, backend/utils/event_bus.py | M3-02, M4-03 | 3 | Pending | Sprint 4

## Member_2_Database
MEMBER 2: DATABASE & DATA PLATFORM ENGINEER
Scope: Full Supabase PostgreSQL Schema (11 Tables), RLS, CRUD Repositories, Auth APIs
Task ID | Module / Subsystem | Detailed Task Description & Deliverables | Files / Symbols Owned | Dependencies | Est. Days | Status | Sprint
M2-01 | Core Relational Schema | Design & deploy PostgreSQL schema for candidate & session lifecycle tables: 1. users, 2. interview_blueprints, 3. interview_sessions, 4. interview_questions, 5. candidate_answers | backend/database/schema.sql, backend/database/migrations/001_core.sql |  | 3 | In Progress | Sprint 1
M2-02 | Evaluation & Speech Schema | Design & deploy PostgreSQL schema for scoring, coaching, and speech tasks: 6. score_dimensions, 7. scores, 8. turn_feedback, 9. interview_reports, 10. recommended_resources, 11. speech_tasks | backend/database/schema.sql, backend/database/migrations/002_analytics.sql | M2-01 | 3 | In Progress | Sprint 1
M2-03 | Supabase Client & CRUD Manager | Build asynchronous DatabaseManager providing full CRUD operations, relations, and session persistence across all 11 tables | backend/database/db_manager.py, backend/database/mock_db_manager.py | M2-01, M2-02 | 4 | In Progress | Sprint 2
M2-04 | Security & RLS Policies | Implement Row-Level Security (RLS) policies for user data isolation, foreign key cascading, and automated updated_at triggers | backend/database/schema.sql | M2-02 | 2 | Pending | Sprint 3
M2-05 | Auth API & Token Verification | Build /auth/register, /auth/login, /auth/refresh endpoints and JWT verification helper get_current_user_optional | backend/api/auth_api.py, backend/database/auth_helpers.py | M2-03 | 3 | Pending | Sprint 3
M2-06 | Query Optimization & Indexing | Add composite database indexes on session_id, user_id, status, and created_at for high concurrency | backend/database/schema.sql | M2-04 | 2 | Pending | Sprint 4

## Member_3_Evaluation
MEMBER 3: EVALUATION & AI COACHING AGENT ENGINEER
Scope: Gemini/Groq AgenticCoachAgent, Per-turn Critiques, Scoring Rubrics, Serper Search
Task ID | Module / Subsystem | Detailed Task Description & Deliverables | Files / Symbols Owned | Dependencies | Est. Days | Status | Sprint
M3-01 | LLM Service Configuration | Configure LLMService supporting Google Gemini (ChatGoogleGenerativeAI) as primary and Groq (ChatGroqViaOpenAI) as fallback | backend/services/llm_service.py, backend/utils/llm_utils.py, backend/utils/llm_chain_processor.py |  | 2 | Pending | Sprint 1
M3-02 | Per-Turn Answer Evaluator | Implement AgenticCoachAgent.evaluate_answer() for real-time turn critique, relevance scoring, and STAR framework analysis | backend/agents/agentic_coach.py, backend/agents/templates/coach_templates.py | M3-01 | 3 | Pending | Sprint 2
M3-03 | Multi-Dimensional Scoring Engine | Design evaluation rubrics and compute numerical scores across competencies (Technical Knowledge, Communication, Problem Solving, Culture Fit) | backend/agents/evaluation_rubrics.py, backend/agents/score_calculator.py | M3-02, M2-02 | 3 | Pending | Sprint 2
M3-04 | Post-Interview Report Generator | Build generate_final_summary() compiling overall performance summary, key strengths, areas for improvement, and radar chart metrics | backend/agents/report_generator.py, backend/api/agent_api.py | M3-03, M2-03 | 3 | Pending | Sprint 3
M3-05 | Serper Resource Discovery Tool | Build LearningResourceSearchTool using Serper.dev API to automatically find curated tutorials, videos, and articles based on weak topics | backend/agents/tools/search_tool.py, backend/services/search_service.py, backend/services/search_helpers.py | M3-04 | 3 | Pending | Sprint 3
M3-06 | Evaluation Status Polling API | Implement /interview/final-summary-status, /interview/feedback, and /interview/resources endpoints | backend/api/agent_api.py | M3-04, M3-05 | 2 | Pending | Sprint 4

## Member_4_Voice
MEMBER 4: VOICE & REAL-TIME STREAMING ENGINEER
Scope: Nova 2 Sonic Bedrock HTTP/2 Worker, Gemini 3.8 Live Fallback, WebSocket Audio Gateway
Task ID | Module / Subsystem | Detailed Task Description & Deliverables | Files / Symbols Owned | Dependencies | Est. Days | Status | Sprint
M4-01 | Nova Sonic Subprocess Worker | Implement Amazon Nova 2 Sonic Bedrock HTTP/2 bidirectional streaming worker (Python 3.13 subprocess with JSON-line stdin/stdout) | backend/services/nova_sonic_worker.py, backend/config/__init__.py |  | 4 | In Progress | Sprint 1
M4-02 | Voice Engine Supervisor | Build NovaSonicVoiceEngine and NovaSonicSession process manager with graceful 7.5-minute Bedrock stream auto-renewal | backend/services/nova_sonic_engine.py | M4-01 | 3 | In Progress | Sprint 1
M4-03 | WebSocket Streaming Gateway | Build real-time WebSocket endpoint /api/speech-to-text/stream with connection tracking and audio streaming | backend/api/speech_api.py, backend/api/speech/websocket_processor.py, backend/api/speech/connection_manager.py | M4-02 | 3 | In Progress | Sprint 2
M4-04 | Gemini Live Voice Fallback | Implement real-time speech-to-speech fallback engine using Gemini 3.8 Live API (GeminiVoiceEngine) | backend/services/gemini_voice_engine.py | M4-03 | 3 | Pending | Sprint 2
M4-05 | Audio Protocol & Barge-in | Implement audio chunk encoding/decoding (16kHz PCM in / 24kHz PCM out), interruption detection (barge-in), and turn completion | backend/api/speech/audio_utils.py, backend/api/speech/tts_service.py | M4-03 | 2 | Pending | Sprint 3
M4-06 | Audio Echo Cancellation Gating | Implement server-side audio playback state coordination to prevent acoustic mic feedback loops | backend/api/speech_api.py, backend/services/nova_sonic_engine.py | M4-05, M5-03 | 2 | Pending | Sprint 4

## Member_5_Frontend
MEMBER 5: FRONTEND COCKPIT & UI/UX ENGINEER
Scope: React/Vite Cockpit, WebGL GLSL Oscilloscope Wave, Web Audio PCM Player, Scorecard UI
Task ID | Module / Subsystem | Detailed Task Description & Deliverables | Files / Symbols Owned | Dependencies | Est. Days | Status | Sprint
M5-01 | Active Interview Cockpit UI | Build active interview cockpit screen (InterviewSession.tsx, CockpitChatStream.tsx) with Theme 03 Red & Gold on White design | frontend/src/components/InterviewSession.tsx, frontend/src/components/CockpitChatStream.tsx |  | 3 | In Progress | Sprint 1
M5-02 | WebGL GLSL Audio Visualizer | Implement high-performance WebGL GLSL shader oscilloscope wave rendering real-time mic and AI audio waveforms | frontend/src/components/CockpitAudioWave.tsx | M5-01 | 2 | In Progress | Sprint 1
M5-03 | Web Audio PCM Streaming Player | Build gapless 24kHz PCM audio player with AudioContext and mic transmission gating to eliminate acoustic echo feedback | frontend/src/utils/streamingAudioPlayer.ts, frontend/src/hooks/useVoiceFirstInterview.ts | M5-02, M4-03 | 4 | In Progress | Sprint 2
M5-04 | Post-Interview Scorecard & Report | Build rich candidate results dashboard with competency radar charts, strength/weakness cards, and learning resource links | frontend/src/components/PostInterviewReport.tsx, frontend/src/components/TranscriptDrawer.tsx | M3-04, M5-01 | 3 | Pending | Sprint 3
M5-05 | Candidate Onboarding & Resume Upload | Build configuration form, resume uploader (POST /files/upload-resume), audio I/O device selector modal, and Auth modal | frontend/src/pages/Index.tsx, frontend/src/components/CockpitSettingsModal.tsx, frontend/src/components/AuthModal.tsx | M1-04, M2-05 | 3 | Pending | Sprint 3
M5-06 | State Machine & Polling Hook | Refactor useInterviewSession.ts to manage state transitions (configuring -> interviewing -> post_interview) and auto-poll report | frontend/src/hooks/useInterviewSession.ts, frontend/src/services/api.ts | M1-04, M3-06 | 2 | Pending | Sprint 4